## DPRExport
Is Current Revision | Activity Stream | Is Locked | Activity Group | Activity | Location | DPR Date | Start | Finish | Duration [hh:mm] | Remarks | DPR Revision | [CD] PAX working on task | Comment | [CD] ORSTED Comments | Comment
N | Team 1 | Y | Non-Working Time | Standby (EDT) - Other | Vessel | 2026-06-19 | 2026-06-19 06:00 | 2026-06-19 06:30 |  | Transfer delayed due to 3rd party vessel blocking access to I51 | 1 | 4 |  | Agreed
N | Team 1 | Y | Non-Working Time | Standby (LT) - Transfer to / from Location | A01 | 2026-06-19 | 2026-06-19 06:30 | 2026-06-19 06:35 |  |  | 1 | 4
N | Team 1 | Y | Effective Working Time | HSE - Toolbox Talk | A01 | 2026-06-19 | 2026-06-19 06:35 | 2026-06-19 06:50 |  |  | 1 | 4
N | Team 1 | Y | Effective Working Time | Electrical - Termination | A01 | 2026-06-19 | 2026-06-19 06:50 | 2026-06-19 12:00 |  |  | 1 | 3
N | Team 1 | Y | Effective Working Time | Fibre Optic | A01 | 2026-06-19 | 2026-06-19 06:50 | 2026-06-19 12:00 |  |  | 1 | 1
N | Team 1 | Y | Effective Working Time | Break | A01 | 2026-06-19 | 2026-06-19 12:00 | 2026-06-19 13:00 |  |  | 1 | 4
N | Team 1 | Y | Effective Working Time | Electrical - Termination | A01 | 2026-06-19 | 2026-06-19 13:00 | 2026-06-19 17:30 |  |  | 1 | 3
N | Team 1 | Y | Effective Working Time | Fibre Optic | A01 | 2026-06-19 | 2026-06-19 13:00 | 2026-06-19 17:30 |  |  | 1 | 1
N | Team 1 | Y | Effective Working Time | General husbandry | A01 | 2026-06-19 | 2026-06-19 17:30 | 2026-06-19 17:55 |  |  | 1 | 4
N | Team 1 | Y | Non-Working Time | Standby (LT) - Transfer to / from Location | A01 | 2026-06-19 | 2026-06-19 17:55 | 2026-06-19 18:00 |  |  | 1 | 4
Y | Team 1 | N | Non-Working Time | Standby (EDT) - Waiting on Transfer | Vessel | 2026-06-19 | 2026-06-19 06:00 | 2026-06-19 06:30 |  | Transfer delayed due to 3rd party vessel blocking access to I51 | 2 |  |  | Agreed
Y | Team 1 | N | Non-Working Time | Standby (LT) - Transfer to / from Location | A01 | 2026-06-19 | 2026-06-19 06:30 | 2026-06-19 06:35 |  |  | 2
Y | Team 1 | N | Effective Working Time | Pre-Works Set up / Asset protection | A01 | 2026-06-19 | 2026-06-19 06:50 | 2026-06-19 12:00 |  |  | 2 | 2
Y | Team 1 | N | Extra Work | Variation | A01 | 2026-06-19 | 2026-06-19 06:50 | 2026-06-19 12:00 |  |  | 2 | 2
Y | Team 1 | N | Effective Working Time | Electrical - Termination | A01 | 2026-06-19 | 2026-06-19 13:00 | 2026-06-19 17:30 |  |  | 2
Y | Team 1 | N | Effective Working Time | Fibre Optic | A01 | 2026-06-19 | 2026-06-19 13:00 | 2026-06-19 17:30 |  |  | 2
Y | Team 1 | N | Non-Working Time | Standby (LT) - Transfer to / from Location | A01 | 2026-06-19 | 2026-06-19 17:55 | 2026-06-19 18:00 |  |  | 2
Y | Team 2 | N | Non-Working Time | Transit to/from field | Vessel | 2026-06-21 | 2026-06-21 | 2026-06-21 06:00 |  | Transit to HOW03 windfarm | 1 | 4
Y | Team 1 | N | Non-Working Time | Standby (LT) - Transfer to / from Location | Vessel | 2026-06-21 | 2026-06-21 06:00 | 2026-06-21 06:15 |  | Transfer to A01 | 1 | 4
Y | Team 1 | N | Effective Working Time | Mobilisation | A01 | 2026-06-21 | 2026-06-21 06:15 | 2026-06-21 06:45 |  | Mob equipment | 1 | 4
Y | Team 1 | N | Effective Working Time | TBT / POWRA | A01 | 2026-06-21 | 2026-06-21 06:45 | 2026-06-21 07:00 |  | TBT/Powra | 1 | 4
Y | Team 1 | N | Effective Working Time | Pre-Works Set up / Asset protection | A01 | 2026-06-21 | 2026-06-21 07:00 | 2026-06-21 08:00 |  | In survey 2 Pax / Asset protection 2 Pax | 1 | 4
Y | Team 1 | N | Effective Working Time | Mechanical - Cable stripping | A01 | 2026-06-21 | 2026-06-21 08:00 | 2026-06-21 12:00 |  | both cables stripped | 1 | 4
Y | Team 1 | N | Effective Working Time | Welfare break on location | A01 | 2026-06-21 | 2026-06-21 12:00 | 2026-06-21 12:30 |  | Lunch break | 1 | 4
Y | Team 1 | N | Effective Working Time | Mechanical - Hang-off | A01 | 2026-06-21 | 2026-06-21 12:30 | 2026-06-21 15:00 |  | both hang-offs complete | 1 | 4
Y | Team 1 | N | Effective Working Time | Electrical - Cable routing | A01 | 2026-06-21 | 2026-06-21 15:00 | 2026-06-21 17:00 |  | first trefoils cleats installed on both cables | 1 | 4
Y | Team 1 | N | Effective Working Time | General husbandry | A01 | 2026-06-21 | 2026-06-21 17:00 | 2026-06-21 17:45 |  | housekeeping | 1 | 4
Y | Team 1 | N | Non-Working Time | Standby (LT) - Transfer to / from Location | A01 | 2026-06-21 | 2026-06-21 17:45 | 2026-06-21 18:00 |  | Transfer back to SOV | 1 | 4
Y | Team 2 | N | Non-Working Time | Standby (LT) - Transfer to / from Location | Vessel | 2026-06-21 | 2026-06-21 18:00 | 2026-06-21 18:15 |  | Transfer to A01 | 1 | 4
Y | Team 2 | N | Effective Working Time | TBT / POWRA | A01 | 2026-06-21 | 2026-06-21 18:15 | 2026-06-21 18:30 |  | TBT / Powra | 1 | 4
Y | Team 2 | N | Effective Working Time | Pre-Termination Testing | A01 | 2026-06-21 | 2026-06-21 18:30 | 2026-06-21 21:30 |  | Phase ID, Oversheath, TDR and FO pre term testing complete on A01-B01 | 1 | 4
Y | Team 2 | N | Effective Working Time | Electrical - Cable routing | A01 | 2026-06-21 | 2026-06-21 21:30 | 2026-06-22 |  | Cleat A01-B01 cable | 1 | 4
Y | Team 1 | N | Extra Work | Pre-Termination Testing | A02 | 2026-07-19 | 2026-07-19 00:02 | 2026-07-19 22:00 |  | Testing dates and team | 1
Y | Team 1 | N | Effective Working Time | Pre-Termination Testing | A01 | 2026-07-19 | 2026-07-19 01:05 | 2026-07-19 02:05 |  | Testing date only | 1
Y | Team 1 | N | Effective Working Time | Pre-Termination Testing | A02 | 2026-07-19 | 2026-07-19 02:00 | 2026-07-19 04:00 |  | Testind date and Team 1 | 1
Y | Team 1 | N | Extra Work | Pre-Termination Testing | A02 | 2026-07-19 | 2026-07-19 02:04 | 2026-07-19 03:04 |  | Testind Date only | 1
Y | Team 1 | N | Re-work | Mobilisation | A02 | 2026-07-19 | 2026-07-19 13:00 | 2026-07-19 13:04 |  | testinf date only | 1
Y | Team 1 | N | Extra Work | Variation | Port of Immingham | 2026-07-22 | 2026-07-22 06:00 | 2026-07-22 18:00 |  | VOR-008 | 1 | 8
Y | Team 2 | N | Extra Work | Variation | Port of Immingham | 2026-07-22 | 2026-07-22 06:00 | 2026-07-22 18:00 |  | VOR-008 | 1 | 4
Y | Team 3 | N | Extra Work | Variation | Port of Immingham | 2026-07-22 | 2026-07-22 06:00 | 2026-07-22 18:00 |  | VOR-008 | 1 | 4
Y | Team 4 | N | Extra Work | Variation | Port of Immingham | 2026-07-22 | 2026-07-22 06:00 | 2026-07-22 18:00 |  | VOR-008 | 1 | 4
Y | Team 5 | N | Extra Work | Variation | Port of Immingham | 2026-07-22 | 2026-07-22 06:00 | 2026-07-22 18:00 |  | VOR-008 | 1 | 4
Y | Team 6 | N | Extra Work | Variation | Port of Immingham | 2026-07-22 | 2026-07-22 06:00 | 2026-07-22 18:00 |  | VOR-008 | 1 | 4
Y | Team 7 | N | Extra Work | Variation | Port of Immingham | 2026-07-22 | 2026-07-22 06:00 | 2026-07-22 18:00 |  | VOR-008 | 1 | 4
Y | Team 8 | N | Extra Work | Variation | Port of Immingham | 2026-07-22 | 2026-07-22 06:00 | 2026-07-22 18:00 |  | VOR-008 | 1 | 4
Y | Team 9 | N | Extra Work | Variation | Port of Immingham | 2026-07-22 | 2026-07-22 06:00 | 2026-07-22 18:00 |  | VOR-008 | 1 | 4
Y | Team 10 | N | Extra Work | Variation | Port of Immingham | 2026-07-22 | 2026-07-22 06:00 | 2026-07-22 18:00 |  | VOR-008 | 1 | 4
Y | Team 11 | N | Extra Work | Variation | Port of Immingham | 2026-07-22 | 2026-07-22 06:00 | 2026-07-22 18:00 |  | VOR-008 | 1 | 4
Y | Team 12 | N | Extra Work | Variation | Port of Immingham | 2026-07-22 | 2026-07-22 06:00 | 2026-07-22 18:00 |  | VOR-008 | 1 | 4

## HSE
Is Current Revision | Is Locked | Date | Revision | Accident | Comment | Near Miss | Comment | Damage to Equipment | Comment | Damage to Environment | Comment | Safety Observation | Comment | Toolbox Talks | Comment | Safety Meetings | Comment | Safety Tours/Inductions | Comment | Vessel Inductions | Comment | Substation Inductions | Comment | CP/P Training | Comment | Lifeboat Drills | Comment | Fire Drills | Comment | MOB Drills | Comment | Others | Comment | NCRs | Comment | Summary
N | Y | 2026-06-19 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Y | N | 2026-06-19 | 2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
N | Y | 2026-06-20 | 1
Y | Y | 2026-06-20 | 2
Y | N | 2026-06-21 | 1
Y | N | 2026-06-22 | 1
Y | N | 2026-06-23 | 1
Y | N | 2026-06-24 | 1
Y | N | 2026-06-25 | 1
Y | N | 2026-06-26 | 1
Y | N | 2026-06-27 | 1
Y | N | 2026-06-28 | 1
Y | N | 2026-06-29 | 1
Y | N | 2026-06-30 | 1
Y | N | 2026-07-01 | 1
Y | N | 2026-07-02 | 1
Y | N | 2026-07-03 | 1
Y | N | 2026-07-04 | 1
Y | N | 2026-07-05 | 1
Y | N | 2026-07-06 | 1
Y | N | 2026-07-07 | 1
Y | N | 2026-07-08 | 1
Y | N | 2026-07-09 | 1
Y | N | 2026-07-10 | 1
Y | N | 2026-07-11 | 1
Y | N | 2026-07-12 | 1
Y | N | 2026-07-13 | 1
Y | N | 2026-07-14 | 1
Y | N | 2026-07-15 | 1
Y | N | 2026-07-16 | 1
Y | N | 2026-07-17 | 1
Y | N | 2026-07-18 | 1
Y | N | 2026-07-19 | 1
Y | N | 2026-07-20 | 1
Y | N | 2026-07-21 | 1
Y | N | 2026-07-22 | 1

## Personnel
Is Current Revision | Is Locked | Date | Revision | Team 1 | Comment | Team 2 | Comment | Team 3 | Comment | Team 4 | Comment | Team 5 | Comment | Team 6 | Comment | Team 7 | Comment | Team 8 | Comment | Team 9 | Comment | Team 10 | Comment | Team 11 | Comment | Team 12 | Comment | JDR Management | Comment | Ørsted Management | Comment | Summary
N | Y | 2026-06-19 | 1 | 4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Y | N | 2026-06-19 | 2 | 4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
N | Y | 2026-06-20 | 1
Y | Y | 2026-06-20 | 2
Y | N | 2026-06-21 | 1
Y | N | 2026-06-22 | 1
Y | N | 2026-06-23 | 1
Y | N | 2026-06-24 | 1
Y | N | 2026-06-25 | 1
Y | N | 2026-06-26 | 1
Y | N | 2026-06-27 | 1
Y | N | 2026-06-28 | 1
Y | N | 2026-06-29 | 1
Y | N | 2026-06-30 | 1
Y | N | 2026-07-01 | 1
Y | N | 2026-07-02 | 1
Y | N | 2026-07-03 | 1
Y | N | 2026-07-04 | 1
Y | N | 2026-07-05 | 1
Y | N | 2026-07-06 | 1
Y | N | 2026-07-07 | 1
Y | N | 2026-07-08 | 1
Y | N | 2026-07-09 | 1
Y | N | 2026-07-10 | 1
Y | N | 2026-07-11 | 1
Y | N | 2026-07-12 | 1
Y | N | 2026-07-13 | 1
Y | N | 2026-07-14 | 1
Y | N | 2026-07-15 | 1
Y | N | 2026-07-16 | 1
Y | N | 2026-07-17 | 1
Y | N | 2026-07-18 | 1
Y | N | 2026-07-19 | 1
Y | N | 2026-07-20 | 1
Y | N | 2026-07-21 | 1
Y | N | 2026-07-22 | 1

## Consumables
Is Current Revision | Is Locked | Date | Revision | Summary
N | Y | 2026-06-19 | 1
Y | N | 2026-06-19 | 2
N | Y | 2026-06-20 | 1
Y | Y | 2026-06-20 | 2
Y | N | 2026-06-21 | 1
Y | N | 2026-06-22 | 1
Y | N | 2026-06-23 | 1
Y | N | 2026-06-24 | 1
Y | N | 2026-06-25 | 1
Y | N | 2026-06-26 | 1
Y | N | 2026-06-27 | 1
Y | N | 2026-06-28 | 1
Y | N | 2026-06-29 | 1
Y | N | 2026-06-30 | 1
Y | N | 2026-07-01 | 1
Y | N | 2026-07-02 | 1
Y | N | 2026-07-03 | 1
Y | N | 2026-07-04 | 1
Y | N | 2026-07-05 | 1
Y | N | 2026-07-06 | 1
Y | N | 2026-07-07 | 1
Y | N | 2026-07-08 | 1
Y | N | 2026-07-09 | 1
Y | N | 2026-07-10 | 1
Y | N | 2026-07-11 | 1
Y | N | 2026-07-12 | 1
Y | N | 2026-07-13 | 1
Y | N | 2026-07-14 | 1
Y | N | 2026-07-15 | 1
Y | N | 2026-07-16 | 1
Y | N | 2026-07-17 | 1
Y | N | 2026-07-18 | 1
Y | N | 2026-07-19 | 1
Y | N | 2026-07-20 | 1
Y | N | 2026-07-21 | 1
Y | N | 2026-07-22 | 1

## Summary
Is Current Revision | Is Locked | Date | Revision | Current DPR Summary | Next 24h Planning
Y | N | 2026-06-21 | 1 | Previous 24 A01 - Mob - In survey - Cable stripping complete - Hv terms ongoing AOB - All teams stood down for lightening 1900-2100

## Weather
Is Current Revision | Is Locked | Date | Revision | Comment
N | Y | 2026-06-19 | 1
Y | N | 2026-06-19 | 2
N | Y | 2026-06-20 | 1
Y | Y | 2026-06-20 | 2
Y | N | 2026-06-21 | 1
Y | N | 2026-06-22 | 1
Y | N | 2026-06-23 | 1
Y | N | 2026-06-24 | 1
Y | N | 2026-06-25 | 1
Y | N | 2026-06-26 | 1
Y | N | 2026-06-27 | 1
Y | N | 2026-06-28 | 1
Y | N | 2026-06-29 | 1
Y | N | 2026-06-30 | 1
Y | N | 2026-07-01 | 1
Y | N | 2026-07-02 | 1
Y | N | 2026-07-03 | 1
Y | N | 2026-07-04 | 1
Y | N | 2026-07-05 | 1
Y | N | 2026-07-06 | 1
Y | N | 2026-07-07 | 1
Y | N | 2026-07-08 | 1
Y | N | 2026-07-09 | 1
Y | N | 2026-07-10 | 1
Y | N | 2026-07-11 | 1
Y | N | 2026-07-12 | 1
Y | N | 2026-07-13 | 1
Y | N | 2026-07-14 | 1
Y | N | 2026-07-15 | 1
Y | N | 2026-07-16 | 1
Y | N | 2026-07-17 | 1
Y | N | 2026-07-18 | 1
Y | N | 2026-07-19 | 1
Y | N | 2026-07-20 | 1
Y | N | 2026-07-21 | 1
Y | N | 2026-07-22 | 1

## Attachments
Is Current Revision | Is Locked | DPR Date | Revision | Attachment Name | File Extension | Attachment Location | Upload Date | Comment | Displayed In Report | Activity Group | Activity | Location | Start | Finish